## Actions
Action # | Focus Area | RPS Recommendation | Action | Parties Responsible | Progress | Anticipated Timeline | Count
1 | Montgomery County Police Department (MCPD) Programs | Eliminate SRO programs and corresponding budget lines | Host virtual public hearings on the School Resource Officer (SRO) program on March 2, 2021 and March 4, 2021 | MCSD Board of Education | Complete | Complete | 1
2 | Montgomery County Police Department (MCPD) Programs | Eliminate SRO programs and corresponding budget lines | Remove police from Montgomery County public high schools by fall 2021 school year. Re-assign officers to patrol communities and respond to incidents at schools when needed, which meets MD state requirement for police response plan for the county schools | Montgomery County Police Department, MCSD Board of Education, County Executive's Office | In Progress | 1 year | 1
3 | Montgomery County Police Department (MCPD) Programs | Better data and recordkeeping | Develop an internal citation data system for criminal /civil citations. | Montgomery County Police Department, Montgomery County Council | In Progress | 18 months | 1
4 | Best Practices for Crisis Reponse and Social Services | Implement and/or expand alternative responses to crime | Report published evaluating Montgomery County's capacity to respond to mental health situations. Overall, OLO found that the County uses several research-supported practices to respond to mental health situations and is currently working to reduce reliance on law enforcement for crisis response | Office of Legislative Oversight, Montgomery County Council | Complete | Complete | 1
5 | Alternative Programs to Police and Jail Interactions | Implement and/or expand alternative responses to crime | Propose FY22 funds to create a community-based Homeless Court program | County Executive's Office | Proposed | 1 year | 1
6 | Alternative Programs to Police and Jail Interactions | Implement and/or expand alternative responses to crime | Stakeholders in Montgomery County are currently working to strengthen the County’s behavioral health crisis care system. | Health and Human Services | In Progress | 6 months | 1
7 | Montgomery County Police Department (MCPD) Programs | Implement and/or expand alternative responses to crime | Transfer automated traffic enforcement from the police department to the transportation department | County Executive's Office, Montgomery County Police Department, Department of Transportation | Proposed |  | 1
8 | 911 and 311 Call Responses | Shift certain responsibilities from police to County agencies and community organizations | Expand the 24/7 mobile crisis unit and hire 5 civilian therapists | Health and Human Services, Montgomery County Council | Complete |  | 1
9 | 911 and 311 Call Responses | Shift certain responsibilities from police to County agencies and community organizations | Develop a new Mobile Crisis Team approach, drawing from nationally recognized models like Crisis Assistance Helping Out On The Streets (CAHOOTS) and the Crisis Now programs. | Health and Human Services | In Progress |  | 1
10 | Montgomery County Police Department (MCPD) Programs | Revise law enforcement recruitment, training and public encounters with civilians | Expand training to include Active Bystander Law Enforcement (ABLE) and justice-based policing. | Montgomery County Police Department | Not Yet Started |  | 1
11

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Focus Areas
Number | Name | Priority
1 | 911 and 311 Call Responses | to determine community needs and provide guidance for areas of focus for the independent audit of MCPD.
2 | Montgomery County Police Department (MCPD) Budget | to review data and structure
3 | Montgomery County Police Department (MCPD) Programs | to review local information as well as programs that have been implemented elsewhere, starting with training and de-escalation.
4 | Alternative Programs to Police and Jail Interactions | to identify other County departments, non-profit organizations, and agencies to propose alternative procedures, programs, and policies to be considered.
5 | Best Practices for Crisis Reponse and Social Services | to research and propose best practices for the intersection of the health, social services, and crisis response system.

## Parties
Organization | Organization Full Name | Organization Website
MCPD | Montgomery County Police Department | http://www.montgomerycountymd.gov/police
PIO | Montgomery County Public Information Office | https://www.montgomerycountymd.gov/opi/site/contactOfficers.html
ORE | Office of Racial Equity and Social Justice | https://www.montgomerycountymd.gov/ore
COR | Montgomery County Corrections and Rehabilitation | http://www.montgomerycountymd.gov/cor
EXEC | County Executive's Office | http://www.montgomerycountymd.gov/exec/index.html
OEMHS | Office of Emergency Management and Homeland Sercurity | http://www.montgomerycountymd.gov/oemhs
FIN | Montgomery County Finance | http://www.montgomerycountymd.gov/finance
FRS | Fire and Rescue Services | http://www.montgomerycountymd.gov/firerescue
HHS | Health and Human Services | http://www.montgomerycountymd.gov/hhs
DCHA | Housing and Community Affairs | http://www.montgomerycountymd.gov/dhca
HRC | Mongtomery County Human Rights Comission | http://www.montgomerycountymd.gov/humanrights
OMB | Office of Management and Budget | http://www.montgomerycountymd.gov/omb
OLR | Office of Labor Relations | http://montgomerycountymd.gov/olr/
DTS | Department of Technology Services | http://www.montgomerycountymd.gov/dts
MCC | Montgomery County Council | http://www.montgomerycountymd.gov/council
MCS | Sheriff's Office | http://www.mcsheriff.com/
MCPS | Montgomery County Public Schools | http://www.montgomeryschoolsmd.org/
OLO | Office of Legislative Oversight | http://www.montgomerycountymd.gov/olo
BOE | MCSD Board of Education | https://www.montgomeryschoolsmd.org/boe/

## Progress Updates
Number | Date | Update HTML
1 | 2021-02-24 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p>
2